## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | ASCA-01 | As a Data Engineer, I want the initial 30 call data sets to be fully processed (Text - TTS - WAV - STT) so that the data is ready for quality validation. | Must Have | Raw Text Data Collected | Zeba Mukhtar | Done
Sprint 1 | Sprint 1 | ASCA-02 | As a Data Scientist, I want to calculate the Word Error Rate (WER) on the 30 processed call files so that the transcription quality can be accurately measured before model training. | Must Have | User Story ASCA-01 is Done (Processed data is available). | Zeba Mukhtar | Done
Sprint 2 | Sprint 2 | ASCA-03 | As a MLOps Engineer, I want to deploy the selected STT model (Whisper/Conformer) as a production-ready API service so that the NLP pipeline can consume the transcript in real-time. | Must Have | ASCA-02 approved WER and Model selected. | Zeba Mukhtar | Done
Sprint 2 | Sprint 2 | ASCA-04 | As a Data Scientist, I want to implement the Sentiment Analysis pipeline using HuggingFace so that the customer's emotional state can be determined. | Must Have | ASCA-03 (STT API ready). | Zeba Mukhtar | Done
Sprint 2 | Sprint 2 | ASCA-05 | As a Data Scientist, I want to implement Intent Analysis and Entity Extraction (NER) models so that the customer's purpose and key data points are extracted. | Must Have | ASCA-04 Done and STT API ready. | Zeba Mukhtar | Done
Sprint 3 | Sprint 3 | ASCA-06 | As a Prompt Engineer, I want to implement the "Direct Prompting" logic for the LLM (GPT/LLaMA) to generate Suggested Questions and Objection Handling based on M3 outputs. | Must Have | ASCA-05 Done (Full NLP output available). | Zeba Mukhtar | Done
Sprint 3 | Sprint 3 | ASCA-07 | As a Frontend Developer, I want to build the initial real-time Dashboard to display the suggestions generated by the AI Reasoning Layer (ASCA-06). | Must Have | ASCA-06 Logic is stable. | Zeba Mukhtar | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7