## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DE-001 | Test Lead | 31/10/2025 | [M1] Tooling Deviation: CMD was used instead of the standard Jupyter Notebook. | Code Review (Sprint 1) | Data Engineer | Process/Tooling | All M1 code was successfully migrated to Jupyter Notebooks and committed to the version control system, enforcing team standardization. | 2025-03-11 | Closed | Team standardization achieved. Testing for M1 passed on Jupyter.
DE-002 | Data Engineer | 18/11/2025 | [M2] Critical Configuration Missing: No save location was defined for the processed audio files. | Unit Testing (M2-2) | Data Engineer | Functional/Configuration | A configuration variable (OUTPUT_PATH) was added to the Python script. Processed .wav files are now successfully saved to the designated folder. | 19/11/2025 | Closed | Blocker for M3 integration is removed. Unit Test M2-2 is now passing.
DE-003 | Data Scientist | 2025-01-12 | [M3] Incorrect Analysis Scope: Sentiment/Intent/NER was done on the Overall Transcript instead of sentence-level for real-time performance. | Functional Review (M3 Logic) | Data Scientist | Logic/Functional | The NLP pipeline was re-architected to use sentence-by-sentence processing, meeting the real-time latency goal of 1 second. | 2025-02-12 | Closed | Logic now supports the core real-time requirement. E2E latency test successful.
DE-004 | Stakeholder (Instructor) | 2025-10-12 | [M4] Requirement Change: Mandatory Streamlit UI: Stakeholder mandated that the Frontend Dashboard must be built using the Streamlit framework. | Stakeholder Review (M4) | Frontend Developer | Requirement Change / Scope Defect | The Frontend Dashboard was successfully rebuilt and refactored using Streamlit. The Streamlit UI is now fully integrated and tested with the M4 reasoning layer. | 2025-11-12 | Closed | Requirement change implemented and verified. The system is ready for demonstration.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others